## Slide 1
Google Cloud Onboarding Journey
A structured four-phase approach to successful cloud migration and adoption
Phase 1:
Pre-Onboarding
Phase 2:
Dev/PoC
Phase 3:
Promote to UAT
Phase 4:
Production
Report Date: October 20, 2025
Google Cloud Platform

## Slide 2
Phase 1: Pre-Onboarding
Initial phase focusing on strategic planning, establishing organizational structures within Google Cloud, and defining essential security policies to ensure a secure and well-governed environment from the outset.
Define Business Goals & Scope
Establish clear objectives and boundaries for the cloud migration
Form Core Cloud Team
Assemble essential personnel with defined roles and responsibilities
Setup GCP Organization & Folder Structure
Create hierarchical organization and folder structure for resource management
Define IAM & Security Policies
Establish identity access management and security frameworks
Setup Billing Account & Budgets
Configure billing and establish cost management parameters
Foundational Network Design (VPC)
Design and implement the virtual private cloud network architecture
Tentative Timeline: Weeks 1-2

## Slide 3
Phase 2: Onboarding to Dev/PoC
Implementation phase focused on establishing the initial functional environment for development teams. This is where the foundational work begins to take shape, enabling developers to start building and experimenting within Google Cloud.
Create Dev/PoC Project
Set up the development project and initial configuration
Configure Environment Resources
Provision and configure computing resources (GCE, GKE)
Deploy CI/CD Pipeline
Implement continuous integration and deployment system
Initial Data Migration for PoC
Migrate and prepare initial dataset for proof of concept
Implement Basic Monitoring & Logging
Set up essential monitoring and logging capabilities
Developer Training & Walkthrough
Provide training and guidance for development team
Tentative Timeline: Weeks 3-5

## Slide 4
Phase 3: Promote to UAT
Critical bridge between development and production, focusing on validating that the application meets all business and functional requirements before going live. Ensures the solution is robust, stable, and ready for end-users.
Create UAT Project & Environment
Set up isolated UAT environment mirroring production
Deploy Application from Dev
Promote code from development to UAT environment
Prepare & Load Test Data
Set up realistic data for comprehensive testing
Grant Access to Business Testers
Provide permissions to key stakeholders for testing
Execute UAT Test Cases
Run comprehensive business scenario tests
Bug Triage & Remediation
Identify and resolve issues before production
Tentative Timeline: Weeks 6-8

## Slide 5
Phase 4: Production
Final phase marking the culmination of the cloud onboarding journey, focusing on seamless launch and reliable long-term operation of the application within the Google Cloud environment. The primary goal is to ensure stability, performance, and maintainability in a live setting.
Create Production Project & Environment
Set up the final production project and environment
Final Security & Compliance Review
Conduct final security and compliance verification
Production Deployment (Go-Live)
Deploy application to production environment
Configure Advanced Monitoring & Alerting
Set up comprehensive monitoring and alerting
Finalize Backup & DR Plan
Complete backup and disaster recovery planning
Operations Handover & Support
Transfer operations responsibilities and provide support
Tentative Timeline: Weeks 9-10
Google Cloud Onboarding Journey
Phase 4 of 4